## Sheet1
Policy Assistant - Implementation - Back Log
RowID | Category | Sub-Category | Type | Issue ID | Issue / Task | Status | Responsibility | Comments
1 | Chat UI | Backend | Defect | I-01 | Chat prompt disappears after two chats. | Not Started | UI/UX / React Development Team | This looks like a frontend/runtime defect. Investigate composer/thread state, rendering, or assistant-ui configuration.
2 | Chat UI | Backend | Defect | I-02 | Chat messages are maintained only in browser/runtime memory and are lost on reload. | Not Started | UI/UX + App Integration/Data Team | The refresh itself may simply be Vite hot reload during development. The real issue is chat state is only in memory and is not persisted. assistant-ui's default LocalRuntime resets on reload unless persistence is configured.
3 | Chat UI | Backend | Enhancement | I-03 | Conversation/thread IDs and message history are not persisted in durable backend storage. | Not Started | App Integration / Backend Team, with UI support | I would not assign this solely to UI/UX. The backend should own durable conversation/thread identity and storage; the UI consumes it.
4 | Chat UI | UI | Enhancement | I-04 | UI should look more like ChatGPT | Not Started | UI/UX Team | Correct ownership. This is visual/interaction design rather than backend work.
5 | Function App | Hosting | Requirement | I-05 | Deploy Orchestrator to Azure | Not Started | Cloud/DevOps Team + App Integration Team | The App Integration team owns the application, but deployment, configuration, CI/CD and hosting are normally Cloud/DevOps responsibilities.
6 | Chat UI | UI | Enhancement | I-06 | Dark theme / assistant-ui ChatGPT clone | Not Started | UI/UX Team | Correct. I would combine this with I-04 or make I-04 an epic with theme/layout subtasks.
7 | Function App | IAM | Requirement | I-07 | Entra identity for Orchestrator | Not Started | IAM Team + Cloud/App Integration Team | You actually need two identity concepts: user authentication and managed identity for the Function App when it calls Azure services. Azure Functions supports managed identity so secrets do not have to be embedded in the app.
8 | Function App | Web Services | Infrasturcture | I-08 | API Gateway REST frontend | Not Started | Gateway Services + App Integration | Your Azure Function already exposes an HTTP REST endpoint. API Management adds governance, policies, throttling, JWT validation, versioning, analytics, etc.; it is not required merely to make the Function RESTful.
9 | Function App | IAM |  | I-09 | API Gateway SSO | Not Started | IAM + UI/UX + Gateway/App Integration | SSO starts in the web application/user authentication flow, not at the API Gateway alone. Azure Functions/App Service can use Microsoft Entra authentication directly, and APIM can independently validate Entra JWTs.
10 | Chat UI | UI |  | I-10 | Chat history sidebar | Not Started | UI/UX + Backend/Data Team | UI builds the sidebar, but backend persistence supplies the conversations. assistant-ui supports remote thread lists/history adapters for exactly this pattern.
| Chat UI / Integration |  |  | I-11 | React Chat UI must replace the temporary/fake model adapter with calls to the Policy Assistant Azure Function /api/policy-chat. |  | App Integration Team + UI/UX Team
| Data / Persistence |  |  | I-12 | Select and implement durable storage for conversations, threads, messages, timestamps and user ownership. |  | App Integration / Data Team
| IAM |  |  | I-13 | Associate persisted conversations with the authenticated Entra user so one user cannot retrieve another user's chats. |  | IAM + App Integration Team
| Function App / IAM |  |  | I-14 | Enable Function App managed identity and assign the required Azure AI Search/Foundry permissions. |  | IAM + Cloud Team
| Configuration / Security |  |  | I-15 | Move service configuration/secrets out of source code and into Azure Function configuration and/or Key Vault. |  | Cloud/DevOps + IAM/Security
| Chat UI / Networking |  |  | I-16 | Configure production CORS/origin rules between the React application and orchestration API. |  | App Integration + Cloud Team
| Hosting |  |  | I-17 | Deploy the React Chat UI to Azure hosting rather than running only through the local Vite development server. |  | Cloud/DevOps + UI Team
| Observability |  |  | I-18 | Implement Application Insights logging, request correlation, dependency tracking and error monitoring for the orchestrator. |  | Cloud/DevOps + App Integration
| Error Handling |  |  | I-19 | Handle Azure AI Search/LLM timeouts, unavailable services, empty search results and API failures gracefully in the UI. |  | App Integration + UI Team
| Security |  |  | I-20 | Define authentication versus authorization rules for access to the Policy Assistant API. |  | IAM/Security + Architecture
| API Management |  |  | I-21 | Decide whether Azure API Management is actually required for the first release or should be introduced later. |  | Architecture + Gateway Services
| RAG/UI |  |  | I-22 | Return and display policy source/citation metadata with answers. |  | App Integration + UI Team
| DevOps |  |  | I-23 | Establish CI/CD for React UI and Azure Function deployments. |  | DevOps/Cloud Team
| Environment Management |  |  | I-24 | Separate local/dev/test/prod configuration and endpoints. |  | DevOps/Cloud + App Integration

## Sheet2
Proposed ID | Category | Issue / Task | Recommended Responsibility
I-11 | Chat UI / Integration | React Chat UI must replace the temporary/fake model adapter with calls to the Policy Assistant Azure Function /api/policy-chat. | App Integration Team + UI/UX Team
I-12 | Data / Persistence | Select and implement durable storage for conversations, threads, messages, timestamps and user ownership. | App Integration / Data Team
I-13 | IAM | Associate persisted conversations with the authenticated Entra user so one user cannot retrieve another user's chats. | IAM + App Integration Team
I-14 | Function App / IAM | Enable Function App managed identity and assign the required Azure AI Search/Foundry permissions. | IAM + Cloud Team
I-15 | Configuration / Security | Move service configuration/secrets out of source code and into Azure Function configuration and/or Key Vault. | Cloud/DevOps + IAM/Security
I-16 | Chat UI / Networking | Configure production CORS/origin rules between the React application and orchestration API. | App Integration + Cloud Team
I-17 | Hosting | Deploy the React Chat UI to Azure hosting rather than running only through the local Vite development server. | Cloud/DevOps + UI Team
I-18 | Observability | Implement Application Insights logging, request correlation, dependency tracking and error monitoring for the orchestrator. | Cloud/DevOps + App Integration
I-19 | Error Handling | Handle Azure AI Search/LLM timeouts, unavailable services, empty search results and API failures gracefully in the UI. | App Integration + UI Team
I-20 | Security | Define authentication versus authorization rules for access to the Policy Assistant API. | IAM/Security + Architecture
I-21 | API Management | Decide whether Azure API Management is actually required for the first release or should be introduced later. | Architecture + Gateway Services
I-22 | RAG/UI | Return and display policy source/citation metadata with answers. | App Integration + UI Team
I-23 | DevOps | Establish CI/CD for React UI and Azure Function deployments. | DevOps/Cloud Team
I-24 | Environment Management | Separate local/dev/test/prod configuration and endpoints. | DevOps/Cloud + App Integration