## Sheet1
Corporate Policy Assistant Solution Implementation
Sequence | Task | Pipeline Phase | Required Docs | Location | Status | Responsibility | Start Date | Duration | End Date | Description | Comments/Notes
1 | Verify Quotas & Regions | Data Query/Ingestion | * Azure Quotas & LLM and Embeddings Regions Lookup |  | Complete
2 | Implement Azure Blob Storage | Data Ingestion | * Implement Azure Blob Container | C:\...\...\...\...\azure-policy-assistant-rag-solution\implementation\azure-blob-storage-container | Complete
3 | Implement Azure Blob Storage - (Policy Meta Data) | Data Ingestion | * Implement Azure Blob Container - Meta Data | C:\...\...\...\...\azure-policy-assistant-rag-solution\implementation\azure-blob-storage-container | Complete
4 | Implement Micosoft Foundry - (Embeddings Mode) - Note Region | Data Query/Ingestion | * Implement Micosoft Foundry - Embeddings Model | C:\...\...\...\...\azure-policy-assistant-rag-solution\implementation\microsoft-foundry | Complete
5 | Implement Micosoft Foundry - (LLM) - Note Region | Data Query | * Implement Micosoft Foundry - LLM | C:\...\...\...\...\azure-policy-assistant-rag-solution\implementation\microsoft-foundry | Complete
6 | Implement Azure AI Service | Data Query/Ingestion | * Implement Foundry Azure AI Service | C:\...\...\...\Repositories\azure-policy-assistant-rag-solution\implementation\azure-ai-search-service | Complete
7 | Implement Azure AI Service - (Vector Index & Indexer) | Data Query/Ingestion | * Implement Foudry Azure AI Service - (Vector Index & Indexer) | C:\...\...\...\Repositories\azure-policy-assistant-rag-solution\implementation\azure-ai-search-service | Complete
8 | Implement Azure AI Service - (Text Spliter Skill) | Data Ingestion | * Implement Foundry AI Service - (Text Spliter Skill) | C:\...\...\...\Repositories\azure-policy-assistant-rag-solution\implementation\azure-ai-search-service | Complete
9 | Implement Azure AI Service - (Embeddings Skill) | Data Ingestion | * Implement Foundry AI Service - (Embeddings Skill) | C:\...\...\...\Repositories\azure-policy-assistant-rag-solution\implementation\azure-ai-search-service | Complete
10 | Implement Azure Functions - (Policy Assist Orchestrator) | Data Query | * Implement Azure Functions - (Policy Assist Orchestrator) | C:\...\...\...\Repositories\azure-policy-assistant-rag-solution\implementation\azure-functions | Complete
11 | Implement Azure API Gateway Service | Data Query | * Implement Azure API Management Gateway - API Service | C:\...\...\...\Repositories\azure-policy-assistant-rag-solution\implementation\azure-api-gateway-service | Not Started
12 | Implement React Policy Assistant - Chat UI | Data Query | * Develop React Policy Assistant - Chat UI | C:\...\...\...\Repositories\azure-policy-assistant-rag-solution\implementation\react-policy-assist-chat-ui | Complete
13 | Integrate React Policy Assistant with API Gateway - Chat UI | Data Query | * integrate React Policy Assistant - Chat UI with Azure Functions | C:\...\...\...\Repositories\azure-policy-assistant-rag-solution\implementation\react-policy-assist-chat-ui | In Process