## Sheet1
POLICY ASSISTANT - IMPLEMENTATION - BACKLOG
RowID | Priority | Category | Sub-Category | Type | Issue ID | Issue / Task | Status | Responsibility | Comments
1 | P0 | Chat UI | API Integration | Requirement | I-01 | Connect React Chat UI to the Policy Assistant Azure Function /api/policy-chat endpoint and remove the temporary/fake model adapter. | Completed | App Integration / Backend Team + UI/UX / React Team | First integration dependency. Validate request/response contract, conversationId handling, loading state, and returned answer rendering.
2 | P0 | Chat UI | Runtime Stability | Defect | I-02 | Resolve the defect where the chat prompt/composer disappears after approximately two chat interactions. | Completed | UI/UX / React Development Team | Blocking UI defect. Investigate assistant-ui runtime/thread state, component rendering, composer lifecycle, and any state reset after message submission.
3 | P0 | Data / Persistence | Conversation Storage | Architecture / Requirement | I-03 | Select and implement durable storage for conversations, threads, messages, timestamps, and user ownership. | Completed | App Integration / Data Team + Architecture | Required before durable history can work. Define data model, retention, indexing/query pattern, and development versus production storage approach.
4 | P0 | Data / Persistence | Conversation State | Requirement | I-04 | Persist conversation/thread IDs and message history in durable backend storage. | Completed | App Integration / Backend Team, with UI support | Backend should own durable conversation identity and history. The UI should receive/reuse the conversation or thread identifier.
|  |  |  | Requirement | I-04 | Add persistent conversation/message storage. | In Progress |  | Persist chat history, user ID's, conversation ID's and etc in Cosmo database.
|  |  |  | Architecture / Requirement | I-04 | Make the orchestrator load previous messages before calling the LLM. | Not Started |  | Send previous chats along AI Search response and user chat promt to LLM for reasoning and final respoonse generation.
5 | P0 | Security / IAM | Authentication & Authorization | Architecture / Requirement | I-05 | Define authentication and authorization rules for access to the Policy Assistant application and API. | Not Started | IAM / Security Team + Architecture + App Integration | Define who can sign in, token audience/scopes, API authorization rules, role/group usage, and access-denied behavior before implementing SSO.
6 | P0 | Security / IAM | User Authentication / SSO | Requirement | I-06 | Implement Microsoft Entra ID user authentication/SSO for the React Policy Assistant and protect the backend API. | Not Started | IAM / Security Team + UI/UX / React Team + App Integration | Replaces the separate 'API Gateway SSO' task. User SSO should not depend on API Management; APIM can validate tokens later if selected.
7 | P0 | Security / IAM | User Data Authorization | Requirement | I-07 | Associate persisted conversations with the authenticated Entra user so users can access only their own chat history. | Not Started | IAM / Security Team + App Integration / Data Team | Depends on authentication and durable conversation storage. Enforce authorization in the backend, not only in the UI.
8 | P0 | Function App | Managed Identity / RBAC | Requirement | I-08 | Enable the Azure Function App managed identity and assign the required Azure AI Search and Foundry/model permissions. | Not Started | IAM / Security Team + Cloud / DevOps Team | Keep service-to-service identity separate from end-user SSO. Validate least-privilege RBAC for Search and model access.
9 | P0 | Configuration / Security | Secrets & App Settings | Requirement | I-09 | Move service configuration and secrets out of source code into Azure Function application settings and/or Azure Key Vault. | Not Started | Cloud / DevOps Team + IAM / Security Team + App Integration | Use managed identity where possible. Separate non-secret configuration from secrets and avoid committing credentials to source control.
10 | P1 | Chat UI / Networking | CORS & Origins | Requirement | I-10 | Configure CORS/origin rules between the React application and the Policy Assistant orchestration API for deployed environments. | Not Started | App Integration / Backend Team + Cloud / DevOps Team | Configure only required origins. Keep local development origins separate from deployed dev/test/prod origins.
11 | P1 | Application Reliability | Error Handling | Requirement | I-11 | Handle Azure AI Search/model timeouts, service failures, empty retrieval results, and API errors gracefully in the UI and backend. | Not Started | App Integration / Backend Team + UI/UX / React Team | Add actionable user messages, backend exception handling, correlation IDs, appropriate HTTP status codes, and retry behavior only where safe.
12 | P1 | RAG / Chat UI | Sources & Citations | Requirement | I-12 | Return policy source/citation metadata with answers and display it in the React chat UI. | Not Started | App Integration / Backend Team + UI/UX / React Team | Preserve source file/title/path metadata from retrieval through the orchestration response so users can trace answers to policy content.
13 | P1 | Chat UI | Chat History | Enhancement / Requirement | I-13 | Implement a chat-history sidebar that lists prior conversations and allows a user to reopen a selected conversation. | Not Started | UI/UX / React Team + App Integration / Data Team | Depends on durable persistence and user ownership. UI builds the sidebar; backend provides thread listing and message retrieval APIs.
14 | P1 | Chat UI | Refresh / State Recovery | Defect | I-14 | Ensure page refresh or application restart restores the user's active conversation/history instead of losing chat state. | Not Started | UI/UX / React Team + App Integration / Data Team | Treat this as state recovery rather than a Vite-refresh problem. Load persisted conversation state after application startup/authentication.
15 | P1 | Function App | Azure Hosting | Deployment | I-15 | Deploy the Policy Assistant orchestration Azure Function to an Azure Function App and configure production application settings. | Not Started | Cloud / DevOps Team + App Integration / Backend Team | Deploy after identity, configuration, and basic security are defined. Validate health, Function URL, networking, Search/model calls, and logs in Azure.
16 | P1 | Chat UI | Azure Hosting | Deployment | I-16 | Deploy the React Policy Assistant UI to an Azure hosting service instead of running only through the local Vite development server. | Not Started | Cloud / DevOps Team + UI/UX / React Team | Configure deployed API base URL, Entra redirect URIs, CORS, HTTPS, and environment-specific application settings.
17 | P1 | Environment Management | Configuration Separation | Requirement | I-17 | Separate local, development, test, and production configuration and service endpoints. | Not Started | Cloud / DevOps Team + App Integration / Backend Team + UI/UX / React Team | Use environment-specific settings for API URLs, Entra configuration, Search/model resources, CORS origins, logging, and feature flags.
18 | P1 | Observability | Application Insights | Requirement | I-18 | Implement Application Insights logging, request correlation, dependency tracking, and error monitoring for the orchestrator. | Not Started | Cloud / DevOps Team + App Integration / Backend Team | Capture end-to-end request correlation across UI/API/Search/model calls while avoiding sensitive prompt or policy data in logs unless explicitly approved.
19 | P2 | DevOps | CI/CD | Requirement | I-19 | Establish CI/CD pipelines for the React UI and Azure Function deployments. | Not Started | Cloud / DevOps Team | Automate build, tests, configuration validation, and deployment promotion after the deployment model and environments are stable.
20 | P2 | API Management | Architecture Decision | Decision | I-20 | Decide whether Azure API Management is required for the first release or should be introduced in a later phase. | Not Started | Architecture + Gateway Services + Security | The Function already exposes an HTTP API. Select APIM only when gateway governance, policies, throttling, analytics, centralized token validation, or API lifecycle needs justify it.
21 | P2 | API Management | Gateway Implementation | Infrastructure | I-21 | If approved by the architecture decision, place Azure API Management in front of the Policy Assistant Function API and configure the REST API facade. | Not Started | Gateway Services + Cloud / DevOps Team + App Integration | Conditional task. Configure routing, JWT validation/policies, throttling, diagnostics, and backend protection only if APIM is selected.
22 | P3 | Chat UI | Visual Design | Enhancement | I-22 | Improve the Policy Assistant UI so its overall chat experience is more similar to a modern ChatGPT-style interface. | Not Started | UI/UX / React Team | Polish after core functionality is stable. Include spacing, responsive layout, message presentation, composer behavior, navigation, and accessibility.
23 | P3 | Chat UI | Theme | Enhancement | I-23 | Implement a polished dark theme using assistant-ui components and the selected ChatGPT-style visual design. | Not Started | UI/UX / React Team | Treat as a subtask of the broader visual-design enhancement. Confirm accessible contrast and light/dark theme behavior if both are supported.

## Sheet2
Implementation Priority & Ownership Guide
Priority | Meaning | Implementation Guidance
P0 | Critical / Foundational | Implement first. Blocks secure end-to-end operation, persistence, or core application functionality.
P1 | High | Implement after P0 dependencies. Required for a usable, deployable, supportable first release.
P2 | Medium | Important platform/operational capability that can follow the first functional deployment.
P3 | Low / Polish | User-experience enhancement that should not block core functionality or deployment.
Team | Primary Scope | Typical Tasks in This Backlog
UI/UX / React Team | Frontend experience and assistant-ui implementation | Composer, thread UI, history sidebar, themes, citations display, client-side auth integration.
App Integration / Backend Team | Azure Function/API and orchestration logic | API contract, conversation APIs, persistence integration, Search/model calls, error handling.
Data Team | Durable conversation storage and data model | Thread/message schema, retrieval, retention, user ownership.
Cloud / DevOps Team | Azure deployment, environments, operations | Function/UI hosting, app settings, CORS support, CI/CD, observability.
IAM / Security Team | Identity, authentication, authorization, RBAC | Entra SSO, managed identity, least privilege, API authorization, secret handling.
Gateway Services | API gateway capability | APIM routing, token policies, throttling, diagnostics if APIM is selected.
Architecture | Cross-cutting design decisions | APIM decision, persistence approach, security model, deployment sequencing.